## Slide 1
ERP as a Service
Project Roadmap & Phase Plan
Prepared for project owner review · September 2026
Notes: Goal of this session: agree on scope, understand the phase sequence and what gates each phase, and align on timeline and risks.

## Slide 2
What We Are Building
One platform, many client companies, each paying for only what they use
1
Multi-client platform
One system serves many client companies, each with their own isolated, private data.
2
Modular by design
Starting with HR, then adding Accounting, Inventory and CRM. Clients switch modules on and off as needs change.
3
Packs & pricing tiers
Modules are bundled into commercial packs. Upgrades and downgrades take effect immediately.
4
Subscription billing
Recurring payments, automated invoicing, and self-service plan changes.
Notes: Keep this business-level. The technical architecture sits behind these four ideas.

## Slide 3
Key Decisions Already Made
Settled during design review — these shape cost, speed, and what we can sell
Start simple, scale later
All clients share one secure database at launch. Dedicated databases become a premium upsell once a client asks and pays for it.
Faster launch, lower running cost
Instant client onboarding
Creating a new client takes seconds, not hours of setup.
Sales can demo and close same-day
Plan changes apply in seconds
When a client upgrades or downgrades, access updates almost immediately.
No support tickets, no waiting
Downgrades never delete data
Dropping a module locks it, keeping data intact. Re-subscribing restores everything.
Makes returning clients frictionless
Notes: The first decision is the most commercially significant: we deliberately avoided over-building isolation nobody has asked to pay for yet.

## Slide 4
The Plan at a Glance
Nine phases, roughly 5–6 months to first paying client
0
Design
1–2 wk
1
Infrastructure
2–3 wk
2
Login & Security
2 wk
3
Data Foundations
2 wk
4
Core Platform
3–4 wk
5
Billing
2–3 wk
6
ERP Modules
ongoing
7
User Portals
3–4 wk
8
Testing
2 wk
9
Launch
1 wk
Phases run mostly in sequence
ERP modules (Phase 6) can be built in parallel once the platform foundation is in place.
Timeline assumes a stable team
Estimates are engineering effort, not calendar guarantees. Scope changes move the dates.
Notes: Phase 0 and 1 are highlighted in gold as the immediate focus. Be explicit that these are effort estimates.

## Slide 5
Phases 0–2: Foundation
Nothing client-facing yet — this is the groundwork everything else stands on
0
Design & Scope
1–2 weeks
Agree the module list, the pack tiers and pricing, and the technology choices.
GATE TO NEXT PHASE
Module list and pack tiers signed off
1
Infrastructure
2–3 weeks
Build the hosting environment: servers, databases, deployment pipeline, monitoring.
GATE TO NEXT PHASE
A test service deploys automatically end to end
2
Login & Security
2 weeks
Single sign-on for all clients, user roles and permissions, secure token handling.
GATE TO NEXT PHASE
A user can log in and be correctly identified
Notes: The gate is the thing to focus on: each phase is only done when its gate is demonstrably met.

## Slide 6
Phases 3–5: The Commercial Engine
Where clients, packs, and money start flowing through the system
3
Data Foundations
2 weeks
Build and prove the client data separation. Automated tests confirm no client can ever see another's data.
GATE TO NEXT PHASE
Cross-client access tests pass in every build
4
Core Platform
3–4 weeks
Client accounts, module catalogue, packs, subscriptions, upgrades and downgrades, data export.
GATE TO NEXT PHASE
A client can be created, subscribed, and upgraded
5
Billing & Payments
2–3 weeks
Payment provider integration, automated invoicing, failed-payment handling.
GATE TO NEXT PHASE
A real payment completes and invoices correctly
Notes: Phase 3 is short but non-negotiable — it is far harder to retrofit data separation onto a live system.

## Slide 7
Phases 6–9: Product & Launch
Turning the platform into something clients actually log into and use
6
HR Module
ongoing
Build the HR module first — employee records, org structure, leave, attendance. A second module follows immediately after.
HR usable end to end by a real client
7
User Portals
3–4 weeks
The screens clients use: sign-up, subscription management, user admin, billing history. Plus an internal admin portal.
A client can self-serve without support
8
Testing & Hardening
2 weeks
Security review, load testing, full client lifecycle testing from sign-up to cancellation.
No critical issues outstanding
9
Launch
1 week
Go live, monitoring and alerting active, support process in place.
First paying client onboarded
Notes: Gold marks indicate each phase gate. Phase 6 runs in parallel with 7 where team size allows.

## Slide 8
Risks & How We Manage Them
The things most likely to cost us time or money, and the plan for each
HIGH
Scope creep on modules
Each new ERP module adds weeks. We fix the MVP module list in Phase 0 and treat additions as separate decisions.
HIGH
Client data separation failure
A leak between clients would be business-ending. Automated tests run on every code change from Phase 3 onward.
MEDIUM
Payment provider constraints
Regional availability and compliance need confirming early — a blocker here delays Phase 5.
MEDIUM
Financial record retention law
Accounting data may be legally required to be kept for years. Needs legal review before we build deletion.
MEDIUM
Team availability
All estimates assume a stable team. Losing a developer mid-phase shifts dates materially.
Notes: Be candid here. The owner should leave knowing what could move the dates and why.

## Slide 9
Packaging Decisions We Need
Three connected questions — answering one without the others leaves gaps
Context: packs are built from features, not whole modules
This lets you sell HR with or without Payroll, at different price points. It also means every feature boundary is a pricing decision.
1
What should be separately sellable in HR?
Proposed: Employee Records · Leave · Attendance · Payroll — four sellable units.
WHY IT MATTERS
A feature can be split later. Two already sold separately cannot easily be merged.
2
Who decides a new feature belongs in a pack — and who sets the price?
These are deliberately two separate permissions, and they recur every time we ship something new.
WHY IT MATTERS
Without named owners, features ship but sit unpriced and unsellable.
3
Do pack changes reach existing clients, or only new ones?
If we add Payroll to Growth, do current Growth clients get it, or only clients who subscribe from now on?
WHY IT MATTERS
If "only new", packs need versioning — a structural change we must make before building billing.
Notes: Question 3 is the one with structural consequences: pack versioning has to be decided before billing is built, not after.

## Slide 10
What We Need From You Today
Two are agreed — the rest still block Phase 1
1
Confirm: HR first, second module next
HR is agreed. We need to know which module comes second — it shapes how we build the module system.
2
What are the pack tiers and prices?
We need the commercial structure before we can build packs and billing.
3
Confirm the payment provider
Regional availability and compliance must be verified before Phase 5 begins.
4
Approve the timeline and team
Estimates assume a stable team throughout. Changes here move every date after them.
Once these are agreed, infrastructure work begins immediately.
Notes: Close on these four. Everything else in the plan is ready to execute.